## TASKS
PROJECT | TASK_NAME | START_DATE | END_DATE | STATUS | ASSIGNED_TO | COST | BUDGET
Maintain Support Systems | HR software upgrades | 2010-01-01 | 2010-02-27 | Closed | Pam King | 8000 | 7000
Maintain Support Systems | Apply Billing System updates | 2010-01-01 | 2010-02-28 | closed | Russ Sanders | 5000 | 7000
Maintain Support Systems | Investigate new Virus Protection software | 2010-02-15 | 2010-03-23 | Open | Pam King | 1700 | 1500
Maintain Support Systems | Arrange for holiday coverage | 2010-01-10 | 2010-01-12 | Closed | Al Bines | 300 | 500
Email Integration | Complete plan | 2010-02-08 | 2010-02-14 | Closed | Mark Nile | 500 | 750
Email Integration | Check software licenses | 2010-02-12 | 2010-02-13 | Closed | Mark Nile | 200 | 200
Email Integration | Get RFPs for new server | 2010-02-19 | 2010-05-03 | Open | Mark Nile | 4000 | 1000
Email Integration | Purchase backup server | 2010-05-12 | 2010-07-07 | Pending | Al Bines | 3200 | 3000
Train Developers in APEX | Create training workspace | 2009-03-01 | 2009-03-01 | Closed | James Cassidy | 100 | 100
Train Developers in APEX | Publish links to self-study courses | 2009-03-01 | 2009-03-01 | Closed | John Watson | 100 | 100
Train Developers in APEX | Publish development standards | 2009-03-01 | 2009-05-01 | On-Hold | John Watson | 1000 | 2000
Convert Excel Spreadsheet | Collect mission-critical spreadsheets | 2009-03-15 | 2009-11-15 | Open | Pam King | 2500 | 4000
Convert Excel Spreadsheet | Create APEX applications from spreadsheets | 2009-03-20 | 2009-11-30 | Open | James Cassidy | 6000 | 10000
Convert Excel Spreadsheet | Send links to previous spreadsheet owners | 2009-03-25 | 2009-12-05 | Open | Mark Nile | 1000 | 1500
Convert Excel Spreadsheet | Lock spreadsheets | 2009-03-25 | 2009-12-05 | Open | Pam King | 1000 | 1500
Employee Satisfaction Survey | Complete questionaire | 2009-05-18 | 2009-06-01 | On-Hold | Irene Jones | 1200 | 800
Employee Satisfaction Survey | Review with legal | 2009-06-02 | 2009-06-03 | On-Hold | Irene Jones | 200 | 400
Employee Satisfaction Survey | Plan rollout schedule | 2009-06-06 | 2009-06-08 | On-Hold | Irene Jones | 200 | 200
Discussion Forum | Identify owners | 2009-06-19 | 2009-06-22 | Closed | Hank Davis | 200 | 300
Discussion Forum | Install APEX application on internet server | 2009-06-23 | 2009-06-23 | Closed | Hank Davis | 100 | 100
Discussion Forum | Monitor participation | 2009-07-01 | 2009-10-31 | Closed | Hank Davis | 3000 | 1500
Softwatre Projects Tracking | Customize Software Projects software | 2009-07-15 | 2009-07-20 | Closed | Tom Suess | 600 | 1000
Softwatre Projects Tracking | Enter base data (Projects, Milestones, etc.) | 2009-07-23 | 2009-07-24 | Closed | Tom Suess | 200 | 200
Softwatre Projects Tracking | Load current tasks and enhancements | 2009-07-25 | 2009-08-02 | Closed | Tom Suess | 400 | 500
Softwatre Projects Tracking | Conduct project kickoff meeting | 2009-08-05 | 2009-08-05 | Closed | Pam King | 100 | 100
Public Website | Determine host server | 2009-08-06 | 2009-08-07 | Closed | Tiger Scott | 200 | 200
Public Website | Check software licenses | 2009-08-07 | 2009-08-07 | Closed | Tom Suess | 100 | 100
Public Website | Purchase additional software licenses, if needed | 2009-08-10 | 2009-09-01 | On-Hold | Al Bines | 300 | 1000
Public Website | Develop web pages | 2009-08-10 | 2009-09-15 | On-Hold | Tiger Scott | 800 | 2000
Public Website | Plan rollout schedule | 2009-09-17 | 2009-09-17 | On-Hold | Tom Suess | 0 | 100